## 2025 Goals Completion
Targetted Completion Percentage
[10 empty] | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Naren | Juhi | Abhi | Naren | Juhi | Abhi | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours | Tasks | Hours
Category | Activity | DevOps Yearly Estimated Hours | $Benefits Infra/licenses/labor | Description | Notes | Tasks | Owners | Hours Spent | % completion | Jan 22-Feb 4 |  | Feb 5-Feb 18 |  | Feb 19 - Mar 4 |  | Mar 5-Mar 18 |  | Mar 19-Apr 1 |  | Apr 2-Apr 15 |  |  | Apr 16-Apr 29 |  |  | Apr 30-May 13 |  | May 14-May 27 |  | May 28-Jun 10 |  | Jun 11-Jun 24 |  | Jun 25-Jul 8 |  | Jul 9-Jul 22 |  | Jul 23-Aug 5 |  | Aug 6-Aug 19 |  | Aug 20-Sep 2 |  | Spe 3-Sep 16 |  | Spe 17-Sep 30 |  | Oct 1-Oct 14 |  | Oct 15-Oct 28 |  | Oct 29-Nov 11 |  | Nov 12-Nov 25 |  | Nov 26-Dec 9 |  | Dec 10-Dec 23
DevOps C&P | CICD Maturity | 200 | 1 hour labor savings per release/defect deployment |  |  | T1 | Abhishek |  | 0% | [12 empty] | 18 |  |  | 2
[6 empty] | T2 | Naren | [12 empty] | 24 | [6 empty] | 44 | CICD Maturity
DevOps C&P | Automations/Optimization | 640 | 30 mins per day average labor savings |  | 3 | T3 | Megnath | 30 | 7.812% |  |  | TASK-620 | 25 | TASK-594 | 5
[6 empty] | 4 | Abhishek | 10 | [5 empty] | TASK-625 | 10
[6 empty] | 5 | Juhi | 10 | [5 empty] | TASK-629 | 10
[7 empty] | Abhishek | [8 empty] | TASK-633
[7 empty] | Megnath | [8 empty] | TASK-645 | 4
[7 empty] | Megnath | [8 empty] | TASK-644 | 4
[7 empty] | Megnath | [8 empty] | TASK-642 | 6
[7 empty] | Megnath | [8 empty] | TASK-641, 634 | 14
[7 empty] | Abhishek | [8 empty] | TASK-638
DevOps C&P | CoE/CICD | 640 | 2 hours labor savings per release/defect OFE deployment |  | 5 |  | Abhishek | 38 | 5.938% |  |  |  |  | TASK-566 | 20 | TASK-639 | [5 empty] | 18
[7 empty] | Megnath | [6 empty] | TASK-624 | 8 | [11 empty] | 18 | CICD in OFE
[7 empty] | Naren | [8 empty] | TASK-650 | 1
DevOps C&P | CoE/CICD
DevOps C&P | CoE/CICD | 480 | Infra = 192$/per month |  | 1 |  | Abhishek | 68 | 41.46% |  |  | TASK-607 | 20 | TASK-626 | 10 | [6 empty] | 22 |  |  | 16
[7 empty] | Megnath | 111 |  |  |  | TASK-618 | 15 | [13 empty] | 96 | GitHub Action Workflows
[7 empty] | Juhi | 10 | [5 empty] | TASK-623 | 10
[7 empty] | Naren | 10 | [5 empty] | TASK-615 | 10
[7 empty] | Juhi | [8 empty] | TASK-613 | 10
[7 empty] | Juhi | [13 empty] | 12
[7 empty] | Naren | [12 empty] | 30 |  |  | 16
DevOps C&P | CoE/Vulnerabilities | 160 | Compliance |  | 2 |  | Naren | 30 | 62.5% |  |  | TASK-590 | 30
[7 empty] | Naren | 70 | [5 empty] | TASK-621 | 70
[16 empty] | TASK-635 | 30
DevOps C&P | CoE |  |  |  | OTVM and CINCOM are the main COTS applications which need validation for Cloud readiness by Vendor.
DevOps C&P | Documentations | 320 | Determine once implemented. |  |  |  | Juhi | 3 | 1.875% | [5 empty] | 3
[7 empty] | Megnath | 3 | [6 empty] | 3
DevOps C&P | Security/Access Management | 320 | Compliance
DevOps Vulnerability Management | Security Vulnerability Remediation and Regulatory Compliance | 600 | Compliance |  | 1-What else can be done similar to build breakers (XRAY scanning) we implemented 2-BOT creation for what Juhi does manually daily for Prisma reports (120-160hrs) 3-Regularly analyze ServiceNow/GOV Tenable reports (reoccuring) 30 /mth x 12 = 360 4-Build breaker implementation for Prisma scanning (80hrs) |  | Juhi | 30 | 5% |  | 10 |  | 10 |  | 10 | [5 empty] | 8 |  |  | 16
[27 empty] | 24 | Vulnerability
DevOps PLM | PLM | 120 | Compliance |  | 8 hrs / env (15 total envs=10 MT + 5 OM Azure) |  | Juhi | 2 | 1.667% |  |  |  | 2
DevOps PLM | PLM | 120 | Compliance |  | 8 hrs / env | [7 empty] | 4
DevOps PLM | PLM | 20 | Compliance |  | 2 hrs / env |  | Juhi | 24 | 120% |  |  |  | 4 | [7 empty] | 5 |  |  | 2 |  |  | 20 | PLM
DevOps PLM | PLM | 320 | Compliance |  | 160 hrs / env (nonprod/prod-dr) |  | Naman |  |  |  |  | ?? |  | ?? |  | TASK-601
DevOps PLM | PLM | 400 | Compliance |  | 160 hrs / env ( (nonprod/prod-dr) |  | Naman |  |  |  |  | ?? |  | ?? |  | TASK-601
DevOps PLM | PLM | 20 | Compliance |  | infra validation |  | Naman |  |  |  |  | ?? |  | ??
DevOps PLM | PLM | 20 | Compliance |  | infra validation |  | Naman |  |  |  |  | ?? |  | ??
DevOps PLM | PLM | 96 | Compliance |  | 8 hrs/mth AZURE |  | Juhi | 6 | 6.25% |  |  |  | 6
DevOps PLM | PLM | 160 | Compliance |  | 80 hrs / env (nonprod/prod-dr) |  | Naman |  |  |  |  | ?? |  | ?? |  | TASK-611
DevOps PLM | PLM | 150 | Compliance |  | 10 hrs / env |  | Juhi | [16 empty] | 8
DevOps PLM | PLM | 20 | Compliance |  | infra validation
DevOps PLM | PLM | 20 | Compliance |  | infra validation/ support DBA team during data migration
DevOps PLM | PLM | 60 | Compliance |  | 4 hrs / env
DevOps PLM | PLM | 240 | Compliance |  | 4 hrs / 5 AZ envs / mth |  | Juhi | 30 | 12.5% |  |  |  | 14 |  | 16
[7 empty] | Juhi | [13 empty] | 5
Cost Optimization | Cost Savings |  | Infra=$? Per month
DevOps Release Deployments | Release/Defect Fix Deployments | 2400 |  |  | 47 |  | Juhi | 62 | 12.42% | 18 | 36 | 7 | 14 |  |  | 6 | 12 |  |  |  | 6 |  |  | 30
[7 empty] | Megnath | 166 |  | 13 | 26 | 6 | 12 |  |  | 11 | 22 | [9 empty] | 106 | Release/Defect Deployments
[7 empty] | Naren | 32 |  | 3 | 6 | 2 | 4 |  |  | 11 | 22 | Unkown |  | 16 |  |  | 24
[7 empty] | Abhishek | 32 |  | 0 | 0 | 1 | 2 | [8 empty] | 12 |  |  | 18
[7 empty] | Naman | 6 |  | 3 | 6 | 0 | 0
DevOps Support | OMMS Support | 4320 |  |  | 4 resources |  | Juhi | 112 | 14.68% |  | 24 |  | 24 |  | 24 | 20 | 40 |  |  |  | 4 |  |  | 16
[7 empty] | Megnath | 190 |  |  | 24 |  | 24 |  | 24 | 13 | 26 |  |  | 10 | [6 empty] | 92 | OMMS Support
[7 empty] | Naren | 114 |  |  | 24 |  | 24 |  | 24 | 11 | 22 | [5 empty] | 32 |  | 20
[7 empty] | Abhishek | 94 |  |  | 24 |  | 24 |  | 24 | 6 | 12 |  |  |  |  | 10
[7 empty] | Naman | 124 |  |  | 40 |  | 40 |  | 40 | 2 | 4
DevOps Maintenance | Azure Env Enhancements | 500
DevOps Support | HCEP/AEP Support | 150 |  |  |  |  | Naren | [8 empty] | TASK-627 | 30 |  | 30
[7 empty] | Juhi | [8 empty] | TASK-636 | [7 empty] | 8 |  |  | 24 | HCEP Support
[7 empty] | Abhishek | [17 empty] | 8
[7 empty] | Naren | [15 empty] | 8
|  | 12496 | [5 empty] | 1329 |  |  | 220 |  | 273 |  | 268 |  | 259 |  | 30 | 80 | 40 | 80 | 80 | 80 | 64 |  | 362 |  | 0 |  | 0 |  | 0 |  | 0
1440
[17 empty] | 320 |  |  |  | 40 |  |  |  | 16
12480
[27 empty] | 44 | DevOps CICD Maturity
[27 empty] | 18 | DevOps CICD in OFE
[27 empty] | 96 | DevOps GitHub Action Workflows
[27 empty] | 24 | Vulnerability
[27 empty] | 20 | PLM
[27 empty] | 106 | OMMS Release/Defects Deployments
[27 empty] | 92 | OMMS Support
[27 empty] | 24 | HCEP Support
[27 empty] | 56 | PTO
480
Note on D4: Ozer, Ilhan: Get the average number of release deployments per month from RM
Note on C9: Ozer, Ilhan: 2 FTE = 2months
Note on C19: Ozer, Ilhan: 2 FTE = 2months
Note on D19: Ozer, Ilhan: Get the average number of release deployments in OFE per month from RM
Note on C25: Ozer, Ilhan: 2 FTE = 1. 5 month
Note on C32: Ozer, Ilhan: 1 FTE 4 weeks
Note on C42: Ozer, Ilhan: 2FTE 4 weeks research
Note on C47: Ozer, Ilhan: 2FTE 4 weeks research
Note on C73: Ozer, Ilhan: 2x2x50x12
Note on F73: Ozer, Ilhan: 47 deployments / month = Avg of 50
Note on C78: Ozer, Ilhan: 4 x 1080
Note on I95: Ozer, Ilhan: 8 weeks x 40 hrs x 4.5 resources
Note on R96: Ozer, Ilhan: 10 days (3/5-18) 8 hours 4 resources
Note on V96: Ozer, Ilhan: PTO
Note on Z96: Ozer, Ilhan: PTO