## 2025 Goals Completion
Category | Activity | DevOps Yearly Estimated Hours | $Benefits Infra/licenses/labor | Description | Notes | Tasks | Owners | Hours Spent | % completion | Jan 22-Feb 4 |  | Feb 5-Feb 18 |  | Feb 19 - Mar 4 |  | Mar 5-Mar 18 |  | Mar 19-Apr 1 |  | Apr 2-Apr 15 | Apr 16-Apr 29
DevOps C&P | CICD Maturity | 200 | 1 hour labor savings per release/defect deployment | some random description |  | Base image rebuilds | Abhishek |  | 0% | [10 empty] | 5 | 8
[6 empty] | Java code coverage (security related) | Naren | [12 empty] | 5 | 8
DevOps C&P | Automations/Optimization | 640 | 30 mins per day average labor savings | some random description | 3 | Config utility setup in OFE | Megnath | #REF! | #REF! |  |  | TASK-620 | 25 | TASK-594 | 5 |  |  |  |  | 5 | 8
[6 empty] | Gen AI Ollama model | Abhishek | #REF! | [5 empty] | TASK-625 | 10 |  |  |  |  | 5 | 8
[6 empty] | RPA to generate Sonar reports | Juhi | #REF! | [5 empty] | TASK-629 | 10 |  |  |  |  | 5 | 8
[6 empty] | Config Automation for OFE - part2 | Abhishek | [8 empty] | TASK-633 |  |  |  | 5 | 8
[6 empty] | Splunk sending alerts | Megnath | [8 empty] | TASK-645 | 4 |  |  | 5 | 8
[6 empty] | Mongo Start Automation | Megnath | [8 empty] | TASK-644 | 4 |  |  | 5 | 8
[6 empty] | Splunk Dashboard for different error codes | Megnath | [8 empty] | TASK-642 | 6 |  |  | 5 | 8
[6 empty] | Zabbix Alerts in OneView for APM OFE | Megnath | [8 empty] | TASK-641, 634 | 14 |  |  | 5 | 8
[6 empty] | Health Status Monitoring Service - Part 1 | Abhishek | [8 empty] | TASK-638 |  |  |  | 5 | 8
DevOps C&P | CoE/CICD | 640 | 2 hours labor savings per release/defect OFE deployment | some random description | 5 | OFE Watchdog Service | Abhishek | #REF! | #REF! |  |  |  |  | TASK-566 | 20 | TASK-639 |  |  |  | 5 | 8
[6 empty] | Automating OFE Services - Mongo and Mule | Megnath | [6 empty] | TASK-624 | 8 |  |  |  |  | 5 | 8
[6 empty] | Modify MPL to deploy for DMZ Layer | Naren | [8 empty] | TASK-650 | 1 |  |  | 5 | 8
DevOps C&P | CoE/CICD |  |  | some random description | [15 empty] | 5 | 8
DevOps C&P | CoE/CICD | 480 | Infra = 192$/per month | some random description | 1 | Maven CI/CD flows | Abhishek | #REF! | #REF! |  |  | TASK-607 | 20 | TASK-626 | 10 |  |  |  |  | 5 | 8
[6 empty] | Parametrization | Megnath | #REF! |  |  |  | TASK-618 | 15 | [6 empty] | 5 | 8
[6 empty] | Add Snapshot Logic and Prisma | Juhi | #REF! | [5 empty] | TASK-623 | 10 |  |  |  |  | 5 | 8
[6 empty] | DB CICD Enablement | Naren | #REF! | [5 empty] | TASK-615 | 10 |  |  |  |  | 5 | 8
[6 empty] | Mule (onboard using Vars + Secrets) | Juhi | [8 empty] | TASK-613 | 10 |  |  | 5 | 8
[6 empty] | Mule | Juhi | [12 empty] | 5 | 8
[6 empty] | Mule | Naren | [12 empty] | 5 | 8
DevOps C&P | CoE/Vulnerabilities | 160 | Compliance | some random description | 2 | Automated Docker Patching Non OFE | Naren | #REF! | #REF! |  |  | TASK-590 | 30 | [6 empty] | 5 | 8
[6 empty] | Automated Docker Patching Azure | Naren | #REF! | [5 empty] | TASK-621 | 70 |  |  |  |  | 5 | 8
[6 empty] | Automated Docker Patching OFE | [9 empty] | TASK-635 | 30
DevOps C&P | CoE |  |  | some random description | OTVM and CINCOM are the main COTS applications which need validation for Cloud readiness by Vendor.
DevOps C&P | Documentations | 320 | Determine once implemented. | some random description |  |  | Juhi | #REF! | #REF! | [5 empty] | 3 |  |  |  |  | 5 | 8
[7 empty] | Megnath | #REF! | [6 empty] | 3 |  |  |  |  | 5 | 8
DevOps C&P | Security/Access Management | 320 | Compliance | some random description
DevOps Vulnerability Management | Security Vulnerability Remediation and Regulatory Compliance | 600 | Compliance | some random description | 1-What else can be done similar to build breakers (XRAY scanning) we implemented 2-BOT creation for what Juhi does manually daily for Prisma reports (120-160hrs) 3-Regularly analyze ServiceNow/GOV Tenable reports (reoccuring) 30 /mth x 12 = 360 4-Build breaker implementation for Prisma scanning (80hrs) |  | Juhi | #REF! | #REF! |  | 10 |  | 10 |  | 10 |  |  |  |  | 5 | 8
DevOps PLM | PLM | 120 | Compliance | some random description | 8 hrs / env (15 total envs=10 MT + 5 OM Azure) | Built POC server | Juhi | #REF! | #REF! |  |  |  | 2 | [6 empty] | 5 | 8
DevOps PLM | PLM | 120 | Compliance | some random description | 8 hrs / env | [7 empty] | 4
DevOps PLM | PLM | 20 | Compliance | some random description | 2 hrs / env | Setup MTDEV | Juhi | #REF! | #REF! |  |  |  | 4 | [6 empty] | 5 | 8
DevOps PLM | PLM | 320 | Compliance | some random description | 160 hrs / env (nonprod/prod-dr) | MongoDB + OpsManager PLM in OFE | Naman |  |  |  |  | ?? |  | ?? |  | TASK-601 |  |  |  | 5 | 8
DevOps PLM | PLM | 400 | Compliance | some random description | 160 hrs / env ( (nonprod/prod-dr) | MongoDB + OpsManager PLM in OFE | Naman |  |  |  |  | ?? |  | ?? |  | TASK-601 |  |  |  | 5 | 8
DevOps PLM | PLM | 20 | Compliance | some random description | infra validation |  | Naman |  |  |  |  | ?? |  | ?? | [5 empty] | 5 | 8
DevOps PLM | PLM | 20 | Compliance | some random description | infra validation |  | Naman |  |  |  |  | ?? |  | ?? | [5 empty] | 5 | 8
DevOps PLM | PLM | 96 | Compliance | some random description | 8 hrs/mth AZURE |  | Juhi | #REF! | #REF! |  |  |  | 6 | [6 empty] | 5 | 8
DevOps PLM | PLM | 160 | Compliance | some random description | 80 hrs / env (nonprod/prod-dr) | Cincom Installation ¦ OFE (NonProd + Prod) | Naman |  |  |  |  | ?? |  | ?? |  | TASK-611 |  |  |  | 5 | 8
DevOps PLM | PLM | 150 | Compliance | some random description | 10 hrs / env | Cincom | Juhi | [12 empty] | 5 | 8
DevOps PLM | PLM | 20 | Compliance | some random description | infra validation
DevOps PLM | PLM | 20 | Compliance | some random description | infra validation/ support DBA team during data migration
DevOps PLM | PLM | 60 | Compliance | some random description | 4 hrs / env
DevOps PLM | PLM | 240 | Compliance | some random description | 4 hrs / 5 AZ envs / mth |  | Juhi | #REF! | #REF! |  |  |  | 14 |  | 16 |  |  |  |  | 5 | 8
[7 empty] | Juhi | [12 empty] | 5 | 8
Cost Optimization | Cost Savings |  | Infra=$? Per month | some random description
DevOps Release Deployments | Release/Defect Fix Deployments | 2400 |  | some random description | 47 |  | Juhi | #REF! | #REF! | 18 | 36 | 7 | 14 |  |  | 6 | 12 |  |  | 5 | 8
[7 empty] | Megnath | #REF! |  | 13 | 26 | 6 | 12 |  |  | 11 | 22 |  |  | 5 | 8
[7 empty] | Naren | #REF! |  | 3 | 6 | 2 | 4 |  |  | 11 | 22 | Unkown |  | 5 | 8
[7 empty] | Abhishek | #REF! |  | 0 | 0 | 1 | 2 | [6 empty] | 5 | 8
[7 empty] | Naman | #REF! |  | 3 | 6 | 0 | 0 | [6 empty] | 5 | 8
DevOps Support | OMMS Support | 4320 |  | some random description | 4 resources |  | Juhi | #REF! | #REF! |  | 24 |  | 24 |  | 24 | 20 | 40 |  |  | 5 | 8
[7 empty] | Megnath | #REF! |  |  | 24 |  | 24 |  | 24 | 13 | 26 |  |  | 5 | 8
[7 empty] | Naren | #REF! |  |  | 24 |  | 24 |  | 24 | 11 | 22 |  |  | 5 | 8
[7 empty] | Abhishek | #REF! |  |  | 24 |  | 24 |  | 24 | 6 | 12 |  |  | 5 | 8
[7 empty] | Naman | #REF! |  |  | 40 |  | 40 |  | 40 | 2 | 4 |  |  | 5 | 8
[20 empty] | 5 | 8
DevOps Maintenance | Azure Env Enhancements | 500 |  | some random description
DevOps Support | HCEP/AEP Support | 150 |  | some random description |  | HCEP - GH Actions ¦ DB Liquibase | Naren | [8 empty] | TASK-627 | 30 |  | 30 | 5 | 8
[6 empty] | BAM - Update for HCEP | Juhi | [8 empty] | TASK-636 |  |  |  | 5 | 8
[7 empty] | Abhishek | [12 empty] | 5 | 8
[6 empty] | Jenkins | Naren | [12 empty] | 5 | 8
[20 empty] | 5 | 8
Note on D2: Ozer, Ilhan: Get the average number of release deployments per month from RM
Note on C7: Ozer, Ilhan: 2 FTE = 2months
Note on C17: Ozer, Ilhan: 2 FTE = 2months
Note on D17: Ozer, Ilhan: Get the average number of release deployments in OFE per month from RM
Note on C23: Ozer, Ilhan: 2 FTE = 1. 5 month
Note on C30: Ozer, Ilhan: 1 FTE 4 weeks
Note on C40: Ozer, Ilhan: 2FTE 4 weeks research
Note on C45: Ozer, Ilhan: 2FTE 4 weeks research
Note on C71: Ozer, Ilhan: 2x2x50x12
Note on F71: Ozer, Ilhan: 47 deployments / month = Avg of 50
Note on C76: Ozer, Ilhan: 4 x 1080